## 20261014
Project Master Schedule
MMC Cluster Gold Project
Discipline | Year | 2026 |  |  | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030 |  | Remarks
| Month | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
| Description | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Milestones
Common | FEED Start ~ Finish
3D Modeling (30%)
AACE Class 3 Cost Estimation
LSTK Cost Estimation
Engineering
Common | 3D Modeling (30%)
Project Control | Invoicing Procedure
90 Days Look-Ahead Schedule
Level 3 FEED Baseline Schedule
Process | Process Design Basis
Process Design Criteria
Equipment List & Datasheet
Summary of Utilities
Heat and Material Balance
UFD
P&ID
Piping | Piping Design Basis
Piping Material Class Specification / Line Class Index
Piping Line List
Piping Special Item List
Plot Plan
Rotating & Static | Technical Specification
Rotating & Static
Electrical | Electrical Design Basis / Philosophy
Basis of Hazard Area Classification
Electrical Equipment Arrangement Plans / Layouts
Load List & Single Line Diagram
Electrical Equipment(Transformer)
Power | Power Generation System
Instrument | Instrumentation Design Criteria
Instrument Index
Process Control System I/O list
PCS
Valve & In-line Instrument
Civil | Soil Investigation & Topographic Survey
| Preliminary Foundation Design | [41 empty] | 지반조사 후 수행가능
U/G Design
Drainage, Road & Paving Design
Arch. & Structure | Design Basis / Criteria
Standard Drawing
List of Buildings & Shelters
Architectural Conceptual Drawings
FEED (Finish)
FEED (Start)
IFA
IFD
Internal
IFA
IFF
Internal
MR
TBE
MR
TBE
MR
TBE
MR
TBE
MR
TBE
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFI
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFI
IFA
IFF

## Civil
Project Master Schedule
MMC Cluster Gold Project
Discipline | Year | 2026 |  |  | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030 |  | Remarks
| Month | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
| Description | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Milestones
Common | FEED Start ~ Finish
3D Modeling (30%)
AACE Class 3 Cost Estimation
LSTK Cost Estimation
Engineering
Common | 3D Modeling (30%)
Project Control | Invoicing Procedure
90 Days Look-Ahead Schedule
Level 3 FEED Baseline Schedule
Process | Process Design Basis
Process Design Criteria
Equipment List & Datasheet
Summary of Utilities
Heat and Material Balance
UFD
P&ID
Piping | Piping Design Basis
Piping Material Class Specification / Line Class Index
Piping Line List
Piping Special Item List
Plot Plan
Rotating & Static | Technical Specification
Rotating & Static
Electrical | Electrical Design Basis / Philosophy
Basis of Hazard Area Classification
Electrical Equipment Arrangement Plans / Layouts
Load List & Single Line Diagram
Electrical Equipment(Transformer)
Power | Power Generation System
Instrument | Instrumentation Design Criteria
Instrument Index
Process Control System I/O list
PCS
Valve & In-line Instrument
Civil | Soil Investigation & Topographic Survey
| Preliminary Foundation Design | 2028 Apr 18: 기계장치 데이터 접수 +6M | 지반조사 후 수행가능
| Preliminary U/G Design | 2028 Apr 18: 전기 데이터 접수 +8M
| Drainage, Road & Paving Design | 2028 Apr 18: FF 관련 자료 없음
Arch. & Structure | Design Basis / Criteria
Standard Drawing
List of Buildings & Shelters
Architectural Conceptual Drawings
FEED (Finish)
FEED (Start)
IFA
IFD
Internal
IFA
IFF
Internal
MR
TBE
MR
TBE
MR
TBE
MR
TBE
MR
TBE
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFI
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFA
IFF
IFI
IFA
IFF